## Product BackLog
Product Backlog Item | Task | Volunteer | Status
As a / an website visitor I want to view a home page so that I can see the most important content at a glance and quickly understand the site navigation | Task 1 | Michael | Closed
| Task 2 | Ben | Closed
| Task 3 | Ben | In Progress
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | Task 1 | Michael | Closed
| Task 2 | Andrew | Closed
| Task 3 | Andrew | Closed
| Task 4 | Andrew | Closed

## Sprint BackLog
Sprint Start Date |  | Mon |  | 2020-02-17
Sprint Days = | 9
[5 empty] | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26
ID | Description | Sprint # |  |  | M | T | W | T | F | S | S | M | T | W
| Sprint Work Item Description |  | Team Member | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 |  | Day 7 | Day 8 | Day 9
Sprint 1 | Make sample data go from server to device
6 | Graphics support on the client side |  |  | 7
16 | Make the graphics library draw some icon and sample temperature text |  |  | 3
17 | Draw the real weather screen |  |  | 3
7 | Implement support for several days |  |  | 1
8 | Implement support for rain, snow, etc. icons |  |  | 0
9 | City changing support
|  |  |  | 15 | 2020-02-17: 15; 2020-02-18: 14; 2020-02-19: 2
Sprint 2 | Minimal working version
10 | Fetch one day temperature data from the weather provider system
11 | Fetch rain, snow, etc details from the provider
12 | Fetch several days data from the provider
13 | Auto-refresh feature
Sprint 3 | Plug in the real weather data

## Analysis
Calendar Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Date | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26
Total Hours Remaining
Hours Worked Today
Total Hours Worked To Date
Total Worked & Remaining Hours
Average Hours Worked Per Day
Task Hours Pending
Task Hours In Progress
Task Hours Complete
Count of Workitems Pending
Count of Workitems In Progress
Count of Workitems Complete

## Sheet4
Sprint Vision:
Sprint Team | NAME | EMAIL ALIAS | PHONE | MOBILE PHONE | EMAIL
| Name | Email | Phone | Mobile
| unknown | unknown
| unassigned | unassigned